Guide 2. APT Project Development

Capstone Course

Guide 2. APT Project Development

Capstone Course

1. APT Project Progress Summary

Below you will find several fields that you must complete with the requested information.

| APT project progress summary | In this section you must summarize the progress you have made on your APT project. Briefly describe which project activities you have carried out and which specific objectives you have met so far, and how. If you have made adjustments to the objectives or methodology, you must include those sections again in this report, indicating what those adjustments are. LicitaWatch is a private B2B tender platform: the Tender Issuer publishes tenders at no cost, the SME searches, filters and applies, the Tender Issuer approves or rejects and awards, and upon awarding a chat between both parties opens automatically. Only SMEs pay: a free Standard plan (unlimited search, 3 applications per month) and a paid Premium plan (7 applications per month, LicitAsist AI assistant, visibility priority and email alerts for the industry). Progress to date (08-10-2026): • Analysis and planning phase completed: Case Analysis, Impact Mapping, prioritized Product Backlog (16 epics, 18 user stories, 75 story points ≈ 600 h), User Story Mapping and project presentation, all updated with the final business model and the new epics for chat (E15) and profile editing (E16). • Sprint 1 (09-01 to 09-12) and Sprint 2 (09-14 to 09-26) completed: registration and login for SMEs and Tender Issuers, and publishing, searching and filtering of tenders. Both with Sprint Planning, dailies, Sprint Review and Retrospective. • Sprint 3 (09-28 to 10-09) in progress: SME application cycle and review/selection of applicants by the Tender Issuer (E4-H4 and E11-H11, 10 points / 80 h). • Agile management up to date: dailies, Burndown Chart, Impediment Log (12 impediments recorded and managed) and Release Sheet with version v1.0.0 planned for 11-20-2026. Specific objectives met so far: gather and prioritize requirements, define the architecture and the data model, and implement the authentication and tender modules (Sprints 1 and 2). |  |
| --- | --- | --- |
| Objectives | Yes, there were adjustments. General objective: develop LicitaWatch, a private web platform that connects Tender Issuers with SMEs throughout the entire tender cycle (publish, search, apply, award and communicate), with a sustainable monetization model. Adjustments made: • Business model: the Tender Issuer publishes for free and only the SME pays a subscription (free Standard / paid Premium), as it is the largest segment. Search is unlimited on all plans; what is limited is the number of applications per month (3 and 7). • Functional scope: the Tender Issuer–SME chat is added, which opens automatically upon awarding (new Chat API with the bd_chat database), along with profile editing. LicitAsist becomes an exclusive benefit of the Premium plan. • Quality and security: the data model is normalized (industry, region, city, company size and statuses) following the instructor's recommendation. |  |
| Methodology | Yes, there were adjustments. Scrum is kept, but with 6 two-week sprints (Sprint 0 was removed, so work starts directly in Sprint 1 on 09-01-2026) and closing with the v1.0.0 release on 11-20-2026. • Estimation: 1 story point = 8 hours; total 75 points ≈ 600 h distributed as 64, 80, 80, 112, 104 and 160 h per sprint. • Real calendar: holidays are discounted (09-18 and 10-12) and Saturday 09-26 is made up in Sprint 2. • Ceremonies: Sprint Planning, daily on Discord, Sprint Review, Retrospective, Burndown Chart and Impediment Log in every sprint. Definition of Done: functional code without critical errors, unit and integration tests. |  |
| Progress evidence | Describe the evidence you will present in this progress report and justify how this evidence shows the development of the project. If relevant, explain how you safeguarded the quality of your APT Project through aspects specific to your discipline (correct application of methodologies, activities, tools, own resources, etc.). In this section, attach the evidence selected to be evaluated by the instructor. Evidence presented: • Planning documents: Case Analysis, Impact Mapping, prioritized Product Backlog, User Stories and User Story Mapping. They show that requirements were gathered and prioritized using business-value criteria. • Architecture and data: normalized ER model and microservices diagram. They show the technical design of the 6 APIs and their separation by database. • Scrum management: Sprint Planning, Sprint Backlog, daily meeting minutes, Sprint Review and Retrospective for Sprints 1 and 2 (completed) and progress of Sprint 3; Burndown Chart and Impediment Log. They demonstrate iterative execution, hour tracking and continuous improvement. • Release Sheet (v1.0.0) with features, risks and committed date. Quality safeguards: application of Scrum with an explicit Definition of Done, PO validation at each review, unit and integration tests, version control with Git, review of impediments (RUT validation, JWT expiration, duplicate applications and notifications) and retrospectives with improvement actions. |  |
| 2. Work Plan Monitoring |  |  |
| Carefully examine your work plan, focusing especially on the progress status and adjustments columns. |  |  |

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Person responsible | Observations | Progress status | Adjustments |
| IT project management (Scrum) | Case analysis, Impact Mapping, prioritized Product Backlog, user stories and User Story Mapping | Word, Excel, Miro, Discord meetings, project presentation | Before 09-01-2026 | Entire team (led by Daniel Roman) | The team's joint work helped; the change in business model during the analysis made it harder. | Completed | Only the SME pays (Standard/Premium); chat and profile editing epics are added. |
| Software architecture and database design | Microservices design, API Gateway and normalized ER model (6 APIs, one DB per service) | Java, Spring Boot, PostgreSQL, ER diagrams | Before 09-01-2026 and adjustments during the project | Pablo Baez and Daniel Roman | The instructor asked to normalize the data, which forced the model to be redone. | Completed (adjusted) | Normalized ER and new Chat API. |
| Software development (backend and frontend) | Sprint 1: registration and login for SMEs and Tender Issuers (JWT, RBAC, RUT validation) | Spring Boot, React + Vite TypeScript, PostgreSQL, Git, Discord | 09-01 to 09-12-2026 (2 weeks) | Pablo Baez (backend), Gonzalo Palacios (frontend), Daniel Roman (QA and documentation) | Learning curve with JWT and RBAC; RUT format validated late. | Completed | Early validations and unit tests in parallel with development were incorporated. |
| Software development (backend and frontend) | Sprint 2: publishing, searching and filtering of tenders by industry and region | Spring Boot, React, Vite PostgreSQL, Git | 09-14 to 09-26-2026 (2 weeks) | Pablo Baez, Daniel Roman and Gonzalo Palacios | Holiday on 09-18; slow listings with many rows and case-sensitive filter. | Completed | Saturday 09-26 was made up; pagination and indexes were added, and the industry filter became case-insensitive. |
| Software development (backend and frontend) | Sprint 3: SME application (E4-H4) and review/selection of applicants by the Tender Issuer (E11-H11) | Spring Boot, React, Vite PostgreSQL, Git | 09-28 to 10-09-2026 (2 weeks) | Pablo Baez, Daniel Roman and Gonzalo Palacios | Risk of out-of-sync statuses between tender and application, and of duplicate applications from double-clicking. | In progress | The monthly application limit (3 Standard / 7 Premium) is applied instead of requiring an active plan. |
| Software development (backend and frontend) | Sprint 4: tracking of SME applications (E5-H5) and Administrator profile: access, oversight of users, tenders and sales (E12-H12, E13-H13) | Spring Boot, React, Vite PostgreSQL, Git | 10-13 to 10-23-2026 (2 weeks) | Pablo Baez, Daniel Roman and Gonzalo Palacios | It is the heaviest sprint (112 h) and slightly exceeds capacity; broad scope of the administration panel. | Not started | The essentials of the panel are prioritized and the workload is monitored in the daily. |
| Software development (backend and frontend) | Sprint 5: Tender Issuer–SME chat upon awarding, profile editing and email notifications | Spring Boot, React, Vite PostgreSQL (bd_chat), Git | 10-26 to 11-06-2026 (2 weeks) | Pablo Baez (Chat API), Gonzalo Palacios (frontend), Daniel Roman (testing) | Risk of duplicate notifications and of synchronization between services. | Not started | Notification deduplication was added to the planning. |
| External services integration and deployment | Sprint 6: Standard/Premium plans with payment gateway (sandbox), LicitAsist assistant (Groq), final testing and v1.0.0 release | Sandbox payment gateway, Groq API, ngrok | 11-09 to 11-20-2026 (2 weeks) | Pablo Baez, Daniel Roman and Gonzalo Palacios | Groq free-plan limit, sandbox credentials and webhook in local environment. | Not started | Caching and AI usage control; load and automated tests planned before the release. |
| Agile management and quality control | Sprint Planning, dailies, Sprint Review, Retrospective, Burndown Chart, Impediment Log and Release Sheet | Discord, Excel, Word, PowerPoint | Continuous, 09-01 to 11-20-2026 | Daniel Roman (Scrum Master), with the entire team | Retrospectives allow quick correction; the impediment log provides traceability. | In progress | All documents were updated to the real calendar and the final scope. |

3. Adjustments Based on Monitoring

Go deeper into the observations of your work plan. Analyze the planned activities and indicate which aspects facilitated or hindered the execution of the plan. Explain how you addressed and/or will address the obstacles. Finally, indicate the adjustments you made to the work plan based on this analysis.

Factors that have facilitated and/or hindered the development of my work plan: Describe the factors that have facilitated and/or hindered the development of your APT Project so far. For difficulties, you must describe what actions you took and/or will take to solve them. Facilitators: • Scrum methodology with clear ceremonies (planning, daily, review and retrospective), shared Definition of Done and a backlog prioritized by the PO. • Small team with defined roles (Pablo on backend and PO, Gonzalo on frontend, Daniel as Scrum Master) and daily communication through Discord. • Microservices architecture with one database per service, which allows working in parallel without blocking each other, and a familiar stack (Java/Spring Boot, React, PostgreSQL). • Tracking with the Burndown Chart and Impediment Log, which helped detect problems early. Difficulties and actions: • Changes in scope and business model (only the SME pays, Standard/Premium plans, chat upon awarding, profile editing): all documents and the backlog were updated, and the new items were placed in Sprint 5 without creating a Sprint 7. • Data model normalization requested by the instructor: the ER was redone. • Learning curve with JWT/RBAC and late RUT validation (Sprint 1): validations were moved earlier and unit tests are now written along with each task. • Holidays (09-18 and 10-12) that reduce working days: the calendar was recalculated and Saturday 09-26 was made up. • Performance, outdated statuses and duplicates (slow listings, double-click when applying, repeated notifications): pagination, indexes, button locking and deduplication were added. • High workload in Sprint 4 (112 h) and external dependencies (Groq free limit, sandbox gateway, local webhook with ngrok): the workload will be watched in each daily, essential stories will be prioritized and integrations will be tested before Sprint 6.

Adjusted or eliminated activities: Indicate the adjustments you made to your work plan or activities you eliminated, and justify why you did so. If your work plan has not required and does not require adjustments, justify this decision based on the facilitators that have allowed you to carry it out as planned. Adjusted activities: • Sprint 0: eliminated. The project starts directly in Sprint 1 (09-01-2026) and the work plan has 6 two-week sprints. • Sprint 5 scope: the Tender Issuer–SME chat (opens upon awarding) and profile editing (epics E15 and E16) were incorporated, without creating a Sprint 7. • Business model and monetization: only the SME pays; the Standard and Premium plans were defined, and the limit applies to monthly applications (3 and 7) instead of requiring an active plan to apply. • Data model: it was normalized (ER v3 to v7) and the Chat API was added with its own database. • Calendar: sprint dates were adjusted for the holidays of 09-18 and 10-12, with a make-up day on Saturday 09-26. Eliminated activities: only Sprint 0. No functionality was removed from the scope; Sprint 4 is kept, prioritizing essential stories if the workload requires it.

Activities not started or delayed: If you have not started activities or they are delayed according to your planning, indicate the reasons why you have not been able to meet those deadlines and what strategies you will use to move forward on those activities without affecting your APT project. No activity already started is delayed in a way that affects delivery: Sprints 1 and 2 closed within plan and Sprint 3 is on track until 10-09-2026. Activities not started (according to planning): • Sprint 4 (10-13 to 10-23), Sprint 5 (10-26 to 11-06) and Sprint 6 (11-09 to 11-20), including the v1.0.0 release: they have not started yet because they depend on closing Sprint 3. Points of attention and strategy: • Sprint 4: it concentrates the heaviest workload of the project and exceeds the estimated capacity. The scope of the Administrator panel will be reordered, prioritizing access and user oversight, and hours will be reviewed in each daily. • Sprint 6: it concentrates the external integrations and the final tests (160 h). The configuration of the sandbox gateway and the Groq API will be brought forward during Sprint 5 and time will be reserved for load and automated tests. • Pending documentation: update the Work Plan and the Gantt Chart to the 6-sprint calendar, and deliver the ER.

In case the APT Project is a group project, this column must indicate the name of the person responsible for each task or activity. This will later allow the evaluation to be differentiated for each team member.